Athy College School Improvement Plan 2013-2016

| YEAR 1 2013 - 2014 |
| --- |
| Summary of main strengths as identified in SSE in May 2013: | ICT availability in all classrooms. Maths available in the school at all levels for JC and LC students Students deciding to do maths / science based courses in 3rd level Team teaching occurring when teaching hours available Arrangement and layout of desks in many classrooms are conducive to group work and active learning methodologies. Several strategies from Instructional Leadership are being implemented successfully by many teachers. |
| Summary of main areas requiring improvement as identified in last SSE: | No resource teacher available that is specific to maths Lack of numerical visual stimuli around the school ____% students taking HL maths at JC level Need to build student’s confidence re numeracy Need to increase their interest and enjoyment of maths• |
| Improvement targets (related to students’ achievement) | Increase by 10% number JC students taking HL and OL maths Students computational skills and level of understanding in the areas of decimals, fractions and percentages will increase by 5% in the areas of addition and subtraction by the end of year 1 The overall interest and enjoyment of students in numeracy will improve and in turn improve their confidence levels when problem solving Improve the numeracy awareness of parents in the lives of their children Create a visually stimulating learning environment throughout the school |
| Required actions (related to Teaching and Learning that will help to achieve the targets) | Extra 2 pages in journal (one for literacy and one for numeracy) where students will write down the key words they come across in literacy and numeracy Definition of numeracy for every classroom wall- laminated Numeracy mini white board in each room Poster to show conversion of fractions to percentages for all subjects re test results laminated in all rooms. Simple trend graphing for students to record and assess their own test results Numeracy Course on moodle – games, videos, apps etc Reinforce parents signing school journals every week. Tutors check journal once a week to make sure they are signed (stamp) Utilise notice boards with glass and frames outside each class room for displaying numeracy related signs |
| Persons responsible | Numeracy core group to lead out. Posters – Fiona and Siobhán Mini whiteboards – Principal will investigate Journals- tutors Moodle – by _____ |
| Timeframe for action | Posters for classrooms – September 2013 Mini whiteboards and notice boards - ready for September 2013 Tutor stamps – to be ordered in September Moodle course - |
| Success criteria/measurable outcomes | 1st year students will be re-assessed for addition/ subtraction skills Analysis of JC student numbers taking HL and OL maths Repeat survey of parents and students re attitudes to numeracy. |
| Review date(s | May 2014 |